## Sheet1
Hazard | Risk | Responsibility | Likelihood | Impact | Response | Control Measures
Virtual Machine goes down | Application goes offline | AWS | 2 | 5 | Start new vm/move to different cloud server | Regularly push changes to GitHub repo
Broken Version of app pushed to github | Application doesn't function properly | Developer | 3 | 5 | Revert to older working version of code | Implement automated unit testing
Ddos attack | Application unavailable to users |  | 3 | 4 | Identify IP addresses with access and update firewall rules | Use multiple firewalls/ check Ips regularly